## UAT Test Plan Overview
NorthBridge Bank — Digital Loan Application System
UAT Test Plan ¦ Prepared by: Ruchitha Yathirajulu ¦ Personal Case Study
Project Name | Digital Loan Application System (DLAS)
Document Type | User Acceptance Testing (UAT) Test Plan
Prepared By | Ruchitha Yathirajulu — Business Analyst
Version | 1.0 — Draft
UAT Start Date | TBD — Scheduled 4 weeks before go-live
UAT End Date | TBD — 2 week testing window
Go-Live Target | Q1 2026
UAT Environment | Staging environment — mirrors production
Sign-off Required By | James Okafor (Product Owner), Sarah Mitchell (Sponsor)
UAT Objectives
✓ Verify that all functional requirements (FR-001 to FR-010) are correctly implemented
✓ Confirm that real end users (loan officers and customers) can complete key workflows without assistance
✓ Validate that the Equifax API integration returns accurate credit scores in under 10 seconds
✓ Confirm that automated SMS and email notifications are triggered correctly at every status change
✓ Ensure the system meets all non-functional requirements — performance, security, and compliance
✓ Obtain formal sign-off from the Product Owner and Project Sponsor before go-live
Entry Criteria (UAT can BEGIN when...) |  | Exit Criteria (UAT is COMPLETE when...)
✓ All functional development is complete and deployed to staging |  | ✓ All test cases have been executed
✓ QA testing is complete with zero critical defects outstanding |  | ✓ All critical and high defects are resolved
✓ UAT test cases are reviewed and approved by the BA |  | ✓ Pass rate of 95% or above is achieved
✓ UAT environment is stable and mirrors production |  | ✓ Product Owner and Sponsor have signed off
✓ Test data is prepared and loaded into staging environment |  | ✓ UAT completion report is submitted

## UAT Test Cases
NorthBridge Bank — UAT Test Cases
Complete all Actual Result and Pass/Fail columns during UAT execution
Test ID | User Story | Test Scenario | Pre-conditions | Test Steps | Expected Result | Actual Result | Pass/Fail | Defect ID | Tester
TC-001 | US-001 | Customer successfully applies for a Personal loan | Customer has a registered and verified account | 1. Log in with valid credentials 2. Click 'Apply for Loan' 3. Select 'Personal Loan' 4. Complete all required fields 5. Upload pay stub and ID 6. Click 'Submit Application' | Application submitted successfully. Confirmation message displayed. Status shows 'Submitted'.
TC-002 | US-001 | System prevents submission with missing required fields | Customer is on the loan application form | 1. Log in with valid credentials 2. Start a new loan application 3. Leave the 'Annual Income' field empty 4. Click 'Submit' | System displays inline error message: 'Annual Income is required'. Form is not submitted.
TC-003 | US-001 | Customer saves application as draft and resumes later | Customer has started but not completed an application | 1. Start a new application 2. Complete first 2 steps only 3. Click 'Save as Draft' 4. Log out 5. Log back in 6. Click 'Resume Application' | Draft application is saved. Customer can resume from where they left off.
TC-004 | US-002 | Customer uploads a valid PDF pay stub | Customer is on the document upload step | 1. Navigate to document upload section 2. Click 'Upload Document' 3. Select a PDF file under 10MB 4. Confirm upload | Document uploaded successfully. File name visible on screen. Status shows 'Document Received'.
TC-005 | US-002 | System rejects file exceeding 10MB size limit | Customer is on the document upload step | 1. Navigate to document upload section 2. Attempt to upload a file larger than 10MB 3. Click upload | System displays error: 'File size exceeds 10MB limit. Please upload a smaller file.'
TC-006 | US-002 | System rejects unsupported file format | Customer is on the document upload step | 1. Navigate to document upload section 2. Attempt to upload a .docx file 3. Click upload | System displays error: 'Unsupported file format. Please upload PDF, JPG, or PNG only.'
TC-007 | US-003 | Customer views real-time application status | Customer has a submitted application | 1. Log in to customer portal 2. Navigate to 'My Applications' 3. Click on the submitted application | Application status displayed correctly as one of: Submitted / Under Review / Approved / Declined.
TC-008 | US-003 | Customer receives SMS and email when status changes | Customer application status changes from Submitted to Under Review | 1. Loan officer opens application on dashboard 2. Loan officer begins review 3. Status updates to 'Under Review' 4. Check customer email and SMS | Customer receives both email and SMS notification within 60 seconds of status change.
TC-009 | US-004 | Loan officer views all assigned applications on dashboard | Loan officer has valid login credentials | 1. Log in as loan officer 2. Navigate to dashboard 3. View list of assigned applications | Dashboard displays all assigned applications with status, date, loan type, and applicant name.
TC-010 | US-004 | Loan officer filters applications by status | Loan officer is on the dashboard with multiple applications | 1. Log in as loan officer 2. Go to dashboard 3. Select filter 'Under Review' 4. Apply filter | Dashboard shows only applications with 'Under Review' status. All other applications are hidden.
TC-011 | US-004 | Equifax credit score displays on application | Application has been submitted by customer | 1. Log in as loan officer 2. Open a submitted application 3. View credit score field | Credit score retrieved from Equifax API is displayed on the application. Score returned in under 10 seconds.
TC-012 | US-005 | Loan officer approves application with reason | Loan officer has reviewed a complete application | 1. Open an application on dashboard 2. Review all details and credit score 3. Select 'Approve' 4. Enter reason: 'All eligibility criteria met' 5. Click 'Confirm Decision' | Application status updates to 'Approved'. Customer receives instant email and SMS notification.
TC-013 | US-005 | System blocks decision without mandatory reason | Loan officer is on the decision screen | 1. Open an application 2. Select 'Decline' 3. Leave reason field empty 4. Click 'Confirm Decision' | System displays error: 'Reason is required before submitting a decision.' Decision is not processed.
TC-014 | US-005 | Application above $50,000 escalates to senior manager | Loan officer is reviewing an application for $75,000 | 1. Open application for $75,000 loan 2. Review details 3. Click 'Approve' | System automatically routes application to senior manager for final approval. Loan officer sees 'Pending Manager Approval' status.
TC-015 | US-006 | Equifax API returns credit score automatically on submission | Customer has submitted a complete loan application | 1. Customer submits application 2. Loan officer opens application on dashboard 3. Check credit score field | Credit score is automatically retrieved and displayed within 10 seconds of submission. No manual action required.
TC-016 | US-006 | System flags application with credit score below 620 | Customer with credit score of 580 submits an application | 1. Customer submits application 2. Equifax API returns score of 580 3. Loan officer views application | Application is automatically flagged with warning: 'Credit score below minimum threshold (620). Manual review required.'

## Defect Log
NorthBridge Bank — UAT Defect Log
Log all defects found during UAT here. All Critical and High defects must be resolved before go-live.
Defect ID | Test Case | Defect Description | Severity | Priority | Assigned To | Status | Resolution
Severity Guide
Critical |  | System crash or data loss — MUST be fixed before go-live
High |  | Major feature broken — MUST be fixed before go-live
Medium |  | Feature works but not as expected — should be fixed before go-live
Low |  | Minor cosmetic issue — can be fixed post go-live

## UAT Sign-off
NorthBridge Bank — UAT Sign-off
By signing below, stakeholders confirm UAT is complete and the system is approved for go-live
UAT Summary
Total Test Cases | 16
Test Cases Passed
Test Cases Failed
Pass Rate
Critical Defects Outstanding
UAT Decision | PASS / FAIL — circle one
Stakeholder Sign-off
Name | Role | Decision | Signature | Date
James Okafor | Product Owner | PASS / FAIL
Sarah Mitchell | Project Sponsor | PASS / FAIL
[Risk Officer] | Compliance Reviewer | PASS / FAIL
Ruchitha Yathirajulu | Business Analyst | PASS / FAIL